## Defect List
Defect ID | Title | Priority | Severity | Status | Release | Module | Platform | Assigned To | Reported By | Start Date | Due Date | Resolved Date | Environment | Detection Phase | Defect Type | Description | Remarks
DEF-001 | Payment gateway charges customer twice on single order | P1 | Critical | Closed | R01 | Payment Module | Flipkart | Priya R | Karthik S | 2025-03-01 | 2025-03-03 | 2025-03-03 | Production | UAT | Functional | HDFC debit card triggered duplicate charge due to gateway callback received twice — no idempotency key | Escalated to payment ops; full refund issued to customer
DEF-002 | Order status stuck at Processing for 72 hours | P2 | High | Closed | R01 | OMS | Meesho | Arjun M | Sneha K | 2025-03-03 | 2025-03-06 | 2025-03-06 | Staging | System Testing | Functional | Scheduler cron job failed due to DB timeout; no shipment update triggered to customer | Customer notified via SMS after manual intervention
DEF-003 | Out-of-stock item allowed through checkout | P2 | High | Resolved | R01 | Inventory Service | Myntra | Sneha K | Priya R | 2025-03-05 | 2025-03-08 | 2025-03-08 | Production | Regression | Data Sync | Real-time sync lag > 15 min between WMS and portal allowed oversell on 23 orders | Manual cancellation done; sync interval reduced to 2 min
DEF-004 | Return window shows expired incorrectly within 10-day period | P2 | High | Open | R02 | Returns Module | Amazon IN | Karthik S | Divya T | 2025-03-07 | 2025-03-12 |  | UAT | UAT | Business Logic | Return eligibility calculated from dispatch date instead of delivery date causing false window-expired error | JIRA ECOM-4521; fix under review
DEF-005 | Double discount applied on flash sale + loyalty coupon combo | P1 | Critical | Closed | R01 | Promotions Engine | Nykaa | Divya T | Arjun M | 2025-03-09 | 2025-03-10 | 2025-03-10 | Production | UAT | Functional | Coupon stacking rule not enforced when flash sale tag present; ₹1.2 L revenue impact | Auto-adjustment applied; mutual-exclusion rule added for promo types
DEF-006 | Order routed to wrong logistics hub causing 3-day delay | P3 | Medium | Closed | R01 | Logistics Engine | Flipkart | Rahul N | Karthik S | 2025-03-10 | 2025-03-13 | 2025-03-13 | Production | System Testing | Data Quality | Stale zone mapping for pin-codes 600001–600050 routed Chennai orders to Bangalore hub | Pin-code master updated; automated zone-validation job added
DEF-007 | Order confirmation email not sent after COD placement | P3 | Medium | In Progress | R02 | Notification Service | Meesho | Ananya B | Sneha K | 2025-03-12 | 2025-03-17 |  | Staging | Regression | Performance | Kafka consumer lag during peak (10k orders/hr) caused notification events to be dropped | Consumer group scaling in progress; interim manual batch notifications
DEF-008 | Mobile number OTP update not saved — session timeout | P3 | Medium | Reopened | R02 | User Profile Service | Myntra | Priya R | Rahul N | 2025-03-14 | 2025-03-18 | 2025-03-18 | UAT | Regression | Functional | Session TTL (30 s) shorter than OTP validation round-trip causing DB commit failure | Reopened after fix failed on iOS Safari; TTL extended to 120 s
DEF-009 | Sponsored products appearing in Newly Launched filter | P4 | Low | Open | R03 | Search Service | Amazon IN | Karthik S | Ananya B | 2025-03-15 | 2025-03-22 |  | QA | Exploratory | UI/UX | Filter query missing exclusion clause for sponsored product flag in newly launched results | Planned for next sprint; raised by seller forum complaint
DEF-010 | Saved address lost when switching app to mobile web | P2 | High | In Progress | R02 | Checkout Service | Nykaa | Sneha K | Divya T | 2025-03-16 | 2025-03-21 |  | Staging | System Testing | Integration | Address ID generated differently across app and mobile-web sessions; affects 12% cross-platform users | Unified ID generation logic in progress; Redis session sync planned
DEF-011 | Refund of ₹4,999 stuck in Initiated state for 7+ days | P1 | Critical | Open | R01 | Refund Engine | Flipkart | Arjun M | Priya R | 2025-03-17 | 2025-03-20 |  | Production | Production | Functional | Refund API timeout not handled — silent failure with no retry or alert; RBI compliance risk | JIRA ECOM-4598; retry with exponential back-off under development
DEF-012 | Seller dashboard GMV showing yesterday's data at 10 AM | P4 | Low | Closed | R02 | Analytics Dashboard | Meesho | Divya T | Karthik S | 2025-03-18 | 2025-03-19 | 2025-03-19 | Production | UAT | Configuration | Dashboard cache TTL incorrectly set to 24 h instead of 15 min; impacted 3.2k seller accounts | Cache TTL corrected; cache-busting on login added